## Product Backlog
Backlog ID | Epic | Backlog Item | Priority | Status
PB-001 | Project Planning | Review assessment requirements | High | Done
PB-002 | Project Planning | Select project topic | High | Done
PB-003 | Project Planning | Select dataset | High | Done
PB-004 | Project Planning | Identify target audience | High | Done
PB-005 | Project Planning | Define overarching research question | High | Done
PB-006 | Project Planning | Define Chart 1 research question | High | Done
PB-007 | Project Planning | Define Chart 2 research question | High | Done
PB-008 | Project Planning | Define Chart 3 research question | High | Done
PB-009 | Project Planning | Define project scope | High | Done
PB-010 | Scrum & Management | Create Scrum structure | High | Done
PB-011 | Scrum & Management | Create Product Backlog | High | Done
PB-012 | Scrum & Management | Create Sprint Backlogs | High | Done
PB-013 | Scrum & Management | Create Trello board | High | Done
PB-014 | Scrum & Management | Add team members | High | Done
PB-015 | Scrum & Management | Conduct Sprint Planning | High | Done
PB-016 | Scrum & Management | Conduct regular team meetings | High | Done
PB-017 | Scrum & Management | Record meeting minutes | High | Done
PB-018 | Scrum & Management | Conduct Sprint Review | High | Done
PB-019 | Scrum & Management | Conduct Sprint Retrospective | High | Done
PB-020 | Scrum & Management | Capture Trello evidence/screenshots | High | Done
PB-021 | Scrum & Management | Maintain Scrum documentation | High | Done
PB-022 | GitHub | Create GitHub repository | High | Done
PB-023 | GitHub | Add team members | High | Done
PB-024 | GitHub | Create project folder structure | High | Done
PB-025 | GitHub | Create README.md | High | Done
PB-026 | GitHub | Add raw dataset/reference | High | Done
PB-027 | GitHub | Add cleaned dataset | High | Done
PB-028 | GitHub | Add prototype files | High | Done
PB-029 | GitHub | Add D3.js source code | High | Done
PB-030 | GitHub | Add documentation | High | Done
PB-031 | GitHub | Commit changes regularly | High | Done
PB-032 | GitHub | Review repository before submission | High | Done
PB-033 | Data | Obtain dataset | High | Done
PB-034 | Data | Inspect dataset structure | High | Done
PB-035 | Data | Check data types | High | Done
PB-036 | Data | Check missing values | High | Done
PB-037 | Data | Check duplicate records | High | Done
PB-038 | Data | Check invalid values | High | Done
PB-039 | Data | Clean text/category values | High | Done
PB-040 | Data | Process required variables | High | Done
PB-041 | Data | Create calculated fields | High | Done
PB-042 | Data | Create data dictionary | High | Done
PB-043 | Data | Validate cleaned dataset | High | Done
PB-044 | Data | Save cleaned dataset | High | Done
PB-045 | Visualisation | Define Chart 1 question | High | Done
PB-046 | Visualisation | Define Chart 2 question | High | Done
PB-047 | Visualisation | Define Chart 3 question | High | Done
PB-048 | Visualisation | Select Chart 1 type | High | Done
PB-049 | Visualisation | Select Chart 2 type | High | Done
PB-050 | Visualisation | Select Chart 3 type | High | Done
PB-051 | Visualisation | Create Chart 1 prototype | High | Done
PB-052 | Visualisation | Create Chart 2 prototype | High | Done
PB-053 | Visualisation | Create Chart 3 prototype | High | Done
PB-054 | Visualisation | Define interactions | High | Done
PB-055 | Visualisation | Review visualisation design | High | Done
PB-056 | Visualisation | Confirm common UI design | High | Done
PB-057 | Development | Set up D3.js v7 | High | Done
PB-058 | Development | Create HTML structure | High | Done
PB-059 | Development | Create CSS | High | Done
PB-060 | Development | Load dataset | High | Done
PB-061 | Development | Develop Chart 1 | High | Done
PB-062 | Development | Develop Chart 2 | High | Done
PB-063 | Development | Develop Chart 3 | High | Done
PB-064 | Development | Add tooltips | High | Done
PB-065 | Development | Add chart interactions | High | Done
PB-066 | Development | Create dashboard layout | High | Done
PB-067 | Development | Add filters | High | Done
PB-068 | Development | Add Reset button | High | Done
PB-069 | Development | Connect charts | High | Done
PB-070 | Development | Synchronise interactions | High | Done
PB-071 | Testing | Functional testing | High | Done
PB-072 | Testing | Data validation | High | Done
PB-073 | Testing | Tooltip testing | High | Done
PB-074 | Testing | Filter testing | High | Done
PB-075 | Testing | Cross-chart testing | High | Done
PB-076 | Testing | Browser testing | High | Done
PB-077 | Testing | Responsive testing | High | Done
PB-078 | Testing | Usability testing | High | Done
PB-079 | Testing | Record bugs | High | Done
PB-080 | Testing | Fix bugs | High | Done
PB-081 | Testing | Retest fixes | High | Done
PB-082 | Testing | Document testing results | High | Done
PB-083 | Finalisation | Final UI review | High | Done
PB-084 | Finalisation | Check chart labels | High | Done
PB-085 | Finalisation | Check axes and legends | High | Done
PB-086 | Finalisation | Check tooltips | High | Done
PB-087 | Finalisation | Check filters | High | Done
PB-088 | Finalisation | Check Reset button | High | Done
PB-089 | Finalisation | Check cross-chart interaction | High | Done
PB-090 | Finalisation | Check responsive layout | High | Done
PB-091 | Finalisation | Verify calculations | High | Done
PB-092 | Finalisation | Check data attribution | High | Done
PB-093 | Finalisation | Document limitations | High | Done
PB-094 | Finalisation | Final team review | High | Done
PB-095 | Finalisation | Prepare submission | High | Done
PB-096 | Documentation | Meeting 01 minutes | High | Done
PB-097 | Documentation | Sprint planning records | High | Done
PB-098 | Documentation | Sprint review records | High | Done
PB-099 | Documentation | Sprint retrospectives | High | Done
PB-100 | Documentation | Testing documentation | High | Done
PB-101 | Documentation | Design rationale | High | Done
PB-102 | Documentation | Design Requirements | High | Done
PB-103 | Documentation | Data cleaning documentation | High | Done
PB-104 | Documentation | README | High | Done
PB-105 | Documentation | GitHub documentation | High | Done
PB-106 | Documentation | Final project documentation | High | Done

## Sprint Task Log
Sprint | Card / Category | Task ID | Task | Priority | Assignee | Status
Sprint 1 | Planning | S1-01 | Review assessment requirements | High | All | Done
Sprint 1 | Planning | S1-02 | Select project topic | High | All | Done
Sprint 1 | Planning | S1-03 | Select dataset | High | All | Done
Sprint 1 | Planning | S1-04 | Identify target audience | High | All | Done
Sprint 1 | Planning | S1-05 | Define overarching research question | High | All | Done
Sprint 1 | Planning | S1-06 | Define Chart 1 research question | High | Samarakoon | Done
Sprint 1 | Planning | S1-07 | Define Chart 2 research question | High | Ilamperuma | Done
Sprint 1 | Planning | S1-08 | Define Chart 3 research question | High | De Silva | Done
Sprint 1 | Visualisation Planning | S1-09 | Select Chart 1 type | High | Samarakoon | Done
Sprint 1 | Visualisation Planning | S1-10 | Select Chart 2 type | High | Ilamperuma | Done
Sprint 1 | Visualisation Planning | S1-11 | Select Chart 3 type | High | De Silva | Done
Sprint 1 | Project Management | S1-12 | Create Trello board | High | Ilamperuma | Done
Sprint 1 | Project Management | S1-13 | Add team members | High | Ilamperuma | Done
Sprint 1 | Project Management | S1-14 | Create GitHub repository | High | Ilamperuma | Done
Sprint 1 | Project Management | S1-15 | Add team members to GitHub | High | Ilamperuma | Done
Sprint 1 | Project Management | S1-16 | Create GitHub folder structure | High | Ilamperuma | Done
Sprint 1 | Data | S1-17 | Initial dataset analysis | High | All | Done
Sprint 1 | Data | S1-18 | Identify missing/duplicate data | High | All | Done
Sprint 1 | Documentation | S1-19 | Prepare Meeting 01 minutes | Medium | Ilamperuma | Done
Sprint 1 | Documentation | S1-20 | Prepare Sprint 1 documentation | Medium | Ilamperuma | Done
Sprint 2 | Data | S2-01 | Complete data cleaning | High | All | Done
Sprint 2 | Data | S2-02 | Process dataset | High | All | Done
Sprint 2 | Data | S2-03 | Create data dictionary | High | All | Done
Sprint 2 | Data | S2-04 | Document data source | High | All | Done
Sprint 2 | Chart 1 | S2-05 | Analyse Chart 1 variables | High | Samarakoon | Done
Sprint 2 | Chart 1 | S2-06 | Create Chart 1 prototype | High | Samarakoon | Done
Sprint 2 | Chart 1 | S2-07 | Decide Chart 1 interactions | High | Samarakoon | Done
Sprint 2 | Chart 1 | S2-08 | Write Chart 1 rationale | High | Samarakoon | Done
Sprint 2 | Chart 2 | S2-09 | Analyse Chart 2 variables | High | Ilamperuma | Done
Sprint 2 | Chart 2 | S2-10 | Create Chart 2 prototype | High | Ilamperuma | Done
Sprint 2 | Chart 2 | S2-11 | Decide Chart 2 interactions | High | Ilamperuma | Done
Sprint 2 | Chart 2 | S2-12 | Write Chart 2 rationale | High | Ilamperuma | Done
Sprint 2 | Chart 3 | S2-13 | Analyse Chart 3 variables | High | De Silva | Done
Sprint 2 | Chart 3 | S2-14 | Create Chart 3 prototype | High | De Silva | Done
Sprint 2 | Chart 3 | S2-15 | Decide Chart 3 interactions | High | De Silva | Done
Sprint 2 | Chart 3 | S2-16 | Write Chart 3 rationale | High | De Silva | Done
Sprint 2 | Team | S2-17 | Review three prototypes together | High | All | Done
Sprint 2 | Team | S2-18 | Confirm common UI design | High | All | Done
Sprint 2 | Team | S2-19 | Prepare progress review | High | All | Done
Sprint 3 | Member 2 | S3-01 | Set up D3.js v7 | High | Ilamperuma | Done
Sprint 3 | Member 1 | S3-02 | Develop Chart 1 | High | Samarakoon | Done
Sprint 3 | Member 1 | S3-03 | Add Chart 1 tooltip | High | Samarakoon | Done
Sprint 3 | Member 1 | S3-04 | Add Chart 1 interaction | High | Samarakoon | Done
Sprint 3 | Member 2 | S3-05 | Develop Chart 2 | High | Ilamperuma | Done
Sprint 3 | Member 2 | S3-06 | Add Chart 2 tooltip | High | Ilamperuma | Done
Sprint 3 | Member 2 | S3-07 | Add Chart 2 interaction | High | Ilamperuma | Done
Sprint 3 | Member 3 | S3-08 | Develop Chart 3 | High | De Silva | Done
Sprint 3 | Member 3 | S3-09 | Add Chart 3 tooltip | High | De Silva | Done
Sprint 3 | Member 3 | S3-10 | Add Chart 3 interaction | High | De Silva | Done
Sprint 3 | Team | S3-11 | Create common CSS | High | All | Done
Sprint 3 | Team | S3-12 | Create initial dashboard | High | All | Done
Sprint 3 | Team | S3-13 | Load common dataset | High | All | Done
Sprint 3 | Team | S3-14 | Check D3.js version | High | All | Done
Sprint 3 | Team | S3-15 | Individual chart review | High | All | Done
Sprint 4 | Integration | S4-01 | Integrate Chart 1 | High | All | Done
Sprint 4 | Integration | S4-02 | Integrate Chart 2 | High | All | Done
Sprint 4 | Integration | S4-03 | Integrate Chart 3 | High | All | Done
Sprint 4 | Integration | S4-04 | Create common dashboard layout | High | All | Done
Sprint 4 | Integration | S4-05 | Add common filters | High | All | Done
Sprint 4 | Integration | S4-06 | Add Reset button | High | All | Done
Sprint 4 | Integration | S4-07 | Connect charts | High | All | Done
Sprint 4 | Integration | S4-08 | Synchronise interactions | High | All | Done
Sprint 4 | Testing | S4-09 | Functional testing | High | All | Done
Sprint 4 | Testing | S4-10 | Data validation | High | All | Done
Sprint 4 | Testing | S4-11 | Tooltip testing | High | All | Done
Sprint 4 | Testing | S4-12 | Filter testing | High | All | Done
Sprint 4 | Testing | S4-13 | Cross-chart testing | High | All | Done
Sprint 4 | Testing | S4-14 | Browser testing | High | All | Done
Sprint 4 | Testing | S4-15 | Responsive testing | High | All | Done
Sprint 4 | Testing | S4-16 | Usability testing | High | All | Done
Sprint 4 | Bug Fixing | S4-17 | Record bugs | High | All | Done
Sprint 4 | Bug Fixing | S4-18 | Fix high-priority bugs | High | All | Done
Sprint 4 | Bug Fixing | S4-19 | Retest fixes | High | All | Done
Sprint 4 | Bug Fixing | S4-20 | Update testing documentation | High | All | Done
Sprint 5 | Final Website | S5-01 | Final UI review | High | All | Done
Sprint 5 | Final Website | S5-02 | Check chart labels | High | All | Done
Sprint 5 | Final Website | S5-03 | Check tooltips | High | All | Done
Sprint 5 | Final Website | S5-04 | Check filters | High | All | Done
Sprint 5 | Final Website | S5-05 | Check Reset button | High | All | Done
Sprint 5 | Final Website | S5-06 | Check cross-chart interaction | High | All | Done
Sprint 5 | Final Website | S5-07 | Check responsive layout | High | All | Done
Sprint 5 | Ethical Review | S5-08 | Check for misleading axes | High | All | Done
Sprint 5 | Ethical Review | S5-09 | Verify calculations | High | All | Done
Sprint 5 | Ethical Review | S5-10 | Check data-source attribution | High | All | Done
Sprint 5 | Ethical Review | S5-11 | Document limitations | High | All | Done
Sprint 5 | Documentation | S5-12 | Complete Scrum documentation | High | Ilamperuma | Done
Sprint 5 | Documentation | S5-13 | Complete meeting minutes | High | Ilamperuma | Done
Sprint 5 | Documentation | S5-14 | Complete testing documentation | High | Ilamperuma | Done
Sprint 5 | Documentation | S5-15 | Complete design rationale documentation | High | Ilamperuma | Done
Sprint 5 | Documentation | S5-16 | Complete design requirements documentation | High | Ilamperuma | Done
Sprint 5 | Documentation | S5-17 | Update README | High | Ilamperuma | Done
Sprint 5 | Final Review & Submission | S5-18 | Check GitHub repository | High | All | Done
Sprint 5 | Final Review & Submission | S5-19 | Final team review | High | All | Done
Sprint 5 | Final Review & Submission | S5-20 | Prepare submission | High | All | Done

## Summary
Team Assignment Summary
Team Member | Role | Tasks Assigned | Status
Ilamperuma | Team Leader / Chart 2 Owner | 22 | Done
Samarakoon | Chart 1 Owner | 10 | Done
De Silva | Chart 3 Owner | 9 | Done
All | Whole-team tasks | 53 | Done
Total Backlog Items: | 106
Total Sprint Tasks: | 94