## Sprint 3 Burndown
Day | Date | Planned Remaining | Actual Remaining | Completed Today | Notes
Day 0 | 2026-10-04 | 15 | 15 | 0 | Sprint 3 starts (Meeting 03, 4 Oct 2026); 15 backlog items planned (S3-01 to S3-15). All items Not Started at kickoff, per Meeting 3 action items; no work closed on Day 0.
Day 1 | 2026-10-05 | 13 | 11 | 4 | Shared D3.js v7 environment set up (S3-01), common dataset loaded (S3-13), D3.js version confirmed (S3-14) and common CSS created (S3-11); all four due Day 1 per Meeting 3 sprint plan.
Day 2 | 2026-10-06 | 10 | 9 | 2 | Chart 1 (S3-02) and Chart 2 (S3-05) D3.js builds closed; due Day 2–3 per Meeting 3 sprint plan.
Day 3 | 2026-10-07 | 8 | 8 | 1 | Chart 3 D3.js build (S3-08) closed, completing the Day 2–3 development window.
Day 4 | 2026-10-08 | 5 | 2 | 6 | Tooltips and interactions closed for all three charts (S3-03, S3-04, S3-06, S3-07, S3-09, S3-10); due Day 4 per Meeting 3 sprint plan.
Day 5 | 2026-10-09 | 3 | 1 | 1 | First-pass dashboard with all three D3.js charts assembled (S3-12); due Day 5.
Day 6 | 2026-10-10 | 0 | 0 | 1 | Sprint end. Individual chart review against research questions and Excel prototypes (S3-15) closed; due end of Week 03. Sprint 3 Backlog fully Done (Product Backlog Sprint Task Log).

## Task Register
ID | Category | Task | Priority | Initial Status | Completed? | Allocated | Day Number
S3-01 | Member 2 | Set up D3.js v7 | High | To Do | Yes | Ilamperuma | 1
S3-02 | Member 1 | Develop Chart 1 | High | To Do | Yes | Samarakoon | 2
S3-03 | Member 1 | Add Chart 1 tooltip | High | To Do | Yes | Samarakoon | 4
S3-04 | Member 1 | Add Chart 1 interaction | High | To Do | Yes | Samarakoon | 4
S3-05 | Member 2 | Develop Chart 2 | High | To Do | Yes | Ilamperuma | 2
S3-06 | Member 2 | Add Chart 2 tooltip | High | To Do | Yes | Ilamperuma | 4
S3-07 | Member 2 | Add Chart 2 interaction | High | To Do | Yes | Ilamperuma | 4
S3-08 | Member 3 | Develop Chart 3 | High | To Do | Yes | De Silva | 3
S3-09 | Member 3 | Add Chart 3 tooltip | High | To Do | Yes | De Silva | 4
S3-10 | Member 3 | Add Chart 3 interaction | High | To Do | Yes | De Silva | 4
S3-11 | Team | Create common CSS | High | To Do | Yes | All | 1
S3-12 | Team | Create initial dashboard | High | To Do | Yes | All | 5
S3-13 | Team | Load common dataset | High | To Do | Yes | All | 1
S3-14 | Team | Check D3.js version | High | To Do | Yes | All | 1
S3-15 | Team | Individual chart review | High | To Do | Yes | All | 6

## Instructions
Item | Instruction
Purpose | Use this workbook as Sprint 3 burndown evidence.
Initial workload | Sprint 3 contains 15 backlog items (S3-01 to S3-15), per the Product Backlog / Sprint Task Log.
Day 0 starting point | Day 0 (4 Oct 2026) reflects Meeting 03 (Sprint 3 kickoff): every Sprint 3 action item was recorded as Not Started, so all 15 items are open on Day 0 and none is closed at kickoff.
Daily update | At the end of each working day, count unchecked Sprint 3 checklist items in Trello and enter that number in Actual Remaining.
Completed Today | This column calculates daily completion from the Actual Remaining values.
Important | Do not invent actual progress. Use the real Trello checklist count.
Chart | The planned and actual lines both update automatically from the table.
Evidence | Keep dated Trello screenshots or board history if your lecturer requires progress evidence.