## Sprint 3
CIS4014-N Interactive Visualisation – Group 4 ¦ Sprint 3 – Week 03
Sprint | Sprint 3
Duration | Week 03 (4 October 2026 – 10 October 2026)
Sprint Goal | Convert each validated Excel prototype into a working D3.js chart with its tooltip and interaction, on a shared D3.js v7 environment and the confirmed common UI design, and assemble a first-pass dashboard ahead of Sprint 4 integration and testing.
Team Leader | Imasha Chathurangi Ilamperuma (F5692459)
Other Team Members | Singappuli Arachchige Isuru Dayanga Samarakoon - F5692600 , Wijaya Hewage Matheesha Priyan Harshana De Silva - F5692734
Project Management Tool | Trello
Version Control | GitHub
Task ID | Sprint Task | Assigned To | Priority | Status | Expected Output | Due | Notes / Evidence | Additional Comments
S3-01 | Set up shared D3.js v7 environment | Ilamperuma | High | Done | Shared, version-pinned D3.js v7 environment confirmed across all three members | 5 Oct 2026 (Day 1) | D3.js v7 selected and pinned; each member's environment checked against it at the Meeting 03 kickoff (Meeting 3, Sprint Plan).
S3-02 | Develop Chart 1 in D3.js | Samarakoon | High | Done | D3.js Temporal Heat Map, 7 days × 15 hourly columns | 6 Oct 2026 (Day 2) | Excel prototype's colour-scale encoding (cell = day/hour, colour intensity = transaction count) rebuilt in D3.js v7. | https://github.com/inkymello/group4-interactive-visualisation/tree/main/charts/Samarakoon
S3-03 | Add Chart 1 tooltip | Samarakoon | High | Done | Chart 1 tooltip showing exact day/hour transaction counts | 8 Oct 2026 (Day 4) | Tooltip added on hover, surfacing the exact count behind each cell's colour intensity.
S3-04 | Add Chart 1 interaction | Samarakoon | High | Done | Hover-to-isolate / click-to-hold interaction implemented | 8 Oct 2026 (Day 4) | Interaction defined in Sprint 2 (Meeting 2, Interactive Features table) implemented in D3.js, highlighting one hour across all seven days. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/design/Interactive_Features_Added_Value.xlsx
S3-05 | Develop Chart 2 in D3.js | Ilamperuma | High | Done | D3.js Store Location Map with ranked store detail | 6 Oct 2026 (Day 2) | Excel prototype's bubble-map encoding (position = geography, bubble size = revenue) rebuilt in D3.js v7. | https://github.com/inkymello/group4-interactive-visualisation/tree/main/charts/Ilamperuma
S3-06 | Add Chart 2 tooltip | Ilamperuma | High | Done | Chart 2 tooltip showing store revenue/transaction detail | 8 Oct 2026 (Day 4) | Tooltip added on hover, surfacing store-level revenue and transaction detail behind each bubble.
S3-07 | Add Chart 2 interaction | Ilamperuma | High | Done | Click-to-filter (with release) interaction implemented | 8 Oct 2026 (Day 4) | Interaction defined in Sprint 2 implemented in D3.js, drilling the page down to a single store and releasing on a second click. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/design/Interactive_Features_Added_Value.xlsx
S3-08 | Develop Chart 3 in D3.js | De Silva | High | Done | D3.js Scatter Plot of daily units sold vs. revenue | 7 Oct 2026 (Day 3) | Excel prototype's scatter encoding (X = quantity_sold, Y = revenue, colour = store_location) rebuilt in D3.js v7. | https://github.com/inkymello/group4-interactive-visualisation/tree/main/charts/De%20Silva
S3-09 | Add Chart 3 tooltip | De Silva | High | Done | Chart 3 tooltip showing daily units/revenue detail | 8 Oct 2026 (Day 4) | Tooltip added on hover, surfacing the daily units-sold and revenue value behind each point.
S3-10 | Add Chart 3 interaction | De Silva | High | Done | Drag-to-zoom box-select interaction implemented | 8 Oct 2026 (Day 4) | Interaction defined in Sprint 2 implemented in D3.js, letting the user box-select a cluster among 56+ store-days plotted. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/design/Interactive_Features_Added_Value.xlsx
S3-11 | Create common CSS | All | High | Done | Shared stylesheet applying the confirmed common UI design | 5 Oct 2026 (Day 1) | Common colour palette, typography and layout from the Sprint 2 UI sign-off (Sprint_3_Meeting_Minutes §11) implemented as shared CSS ahead of individual chart development. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/design/UI_Design_Document.docx
S3-12 | Create initial dashboard | All | High | Done | First-pass dashboard combining all three D3.js charts | 9 Oct 2026 (Day 5) | All three charts placed together on one page for the first time, ahead of full integration and shared filters in Sprint 4. | https://github.com/inkymello/group4-interactive-visualisation/tree/main/dashboard/initial%20dashbaord
S3-13 | Load common dataset | All | High | Done | Cleaned dataset (149,116 rows × 23 columns) loaded into the shared D3.js environment | 5 Oct 2026 (Day 1) | Sprint 2 cleaned and processed dataset loaded and confirmed accessible to all three chart builds.
S3-14 | Check D3.js version | All | High | Done | D3.js v7 compatibility confirmed across all environments | 5 Oct 2026 (Day 1) | Version check completed alongside the shared environment set-up, avoiding mismatch issues before chart development began.
S3-15 | Individual chart review | All | High | Done | Each D3.js chart reviewed against its research question and Excel prototype | 10 Oct 2026 (Day 6) | Each of the three charts checked against its validated Excel prototype figures (e.g. KPI band: $698,812 revenue, 149,116 transactions, 214,470 units) and its research question. . Sprint end. | Progress-review update prepared for Meeting 04.