## Sprint 2
CIS4014-N Interactive Visualisation – Group 4 ¦ Sprint 2 – Week 02
Sprint | Sprint 2
Duration | Week 02 (27 September 2026 – 3 October 2026)
Sprint Goal | Complete data cleaning and documentation, build and validate a working prototype for each of the three charts, and align the team on a common UI design ahead of Sprint 3.
Team Leader | Imasha Chathurangi Ilamperuma (F5692459)
Other Team Members | Singappuli Arachchige Isuru Dayanga Samarakoon - F5692600 , Wijaya Hewage Matheesha Priyan Harshana De Silva - F5692734
Project Management Tool | Trello
Version Control | GitHub
Task ID | Sprint Task | Assigned To | Priority | Status | Expected Output | Due | Notes / Evidence | Additional Comments
S2-01 | Complete data cleaning | All | High | Done | Fully validated, cleaned transaction dataset | 27 Sep 2026 (Day 0) | 149,116-row raw dataset cleaned via the full 20-step Cleaning Log; result passed with 0 missing values, 0 duplicate transaction IDs, 0 duplicate rows, 0 invalid quantities/prices and 0 invalid date/time values (Meeting 2, section 6). Closed at Sprint 2 kickoff. | Fixed corrupted product_category prefix (e.g. "%%%@C0ff33" → "Coffee") identified in Week 01 analysis.
S2-02 | Process dataset | All | High | Done | Derived revenue, coordinate, product-split and calendar fields | 27 Sep 2026 (Day 0) | 13 new derived fields added, taking the dataset to 149,116 rows × 23 columns: revenue, store latitude/longitude, product_type/product_name/size, year/month/month_name, day_of_week, hour, week_of_year (Meeting 2, §6 & §8). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/data/Coffee_Shop%20Sales%20-Cleaned%20and%20Processed%20Data.xlsx
S2-03 | Create data dictionary | All | High | Done | Field-by-field reference for the cleaned dataset | 27 Sep 2026 (Day 0) | Data dictionary completed alongside the cleaning pass, ahead of expectations (Meeting 2, Section 8; Retrospective Section 3). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/data%20cleaning/Data_Cleaning_Document.docx
S2-04 | Document data source | All | High | Done | Short write-up of dataset origin and cleaning approach | 27 Sep 2026 (Day 0) | Dataset origin and 20-step cleaning approach documented and reviewed at kickoff (Meeting 2, Section 8). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/data%20cleaning/Data_Cleaning_Document.docx
S2-05 | Analyse Chart 1 variables | Samarakoon | High | Done | Confirmed variable encoding for Chart 1 (Temporal Heat Map) | 27 Sep 2026 (Day 0) | Encoding confirmed: cell position = day/hour, colour intensity = transaction count, validated against real hourly totals (Meeting 2, Section 5). | Chart 1 ownership changed to Samarakoon
S2-06 | Create Chart 1 prototype | Samarakoon | High | Done | Chart 1 prototype built | 27 Sep 2026 (Day 0) | Built as an Excel-native conditional-formatting colour-scale grid, 7 days × 15 hourly columns (6:00–20:00). File: 1_Heatmap_WhenTheQueueForms.xlsx (Meeting 2, Section 11).
S2-07 | Decide Chart 1 interactions | Samarakoon | High | Done | Chart 1 interactions defined | 27 Sep 2026 (Day 0) | Hover-to-isolate / click-to-hold defined, highlighting one hour across all seven days (Meeting 2, Interactive Features table).
S2-08 | Write Chart 1 rationale | Samarakoon | High | Done | Chart 1 design-rationale note | 27 Sep 2026 (Day 0) | Rationale validated against KPI band: $698,812 revenue, 149,116 transactions, 214,470 units, $4.69 per transaction; busiest hour 10:00 (18,545 transactions) (Meeting 2, Section 5).
S2-09 | Analyse Chart 2 variables | Ilamperuma | High | Done | Confirmed variable encoding for Chart 2 (Store Location Map) | 27 Sep 2026 (Day 0) | Encoding confirmed: position = geography (latitude/longitude), bubble size = revenue (Meeting 2, Section 5). | Chart 2 ownership changed to Ilamperuma
S2-10 | Create Chart 2 prototype | Ilamperuma | High | Done | Chart 2 prototype built | 27 Sep 2026 (Day 0) | Built as an Excel-native bubble chart with a ranked store table. File: 2_StoreMap_WhereTheMoneyLands.xlsx (Meeting 2, Section 11).
S2-11 | Decide Chart 2 interactions | Ilamperuma | High | Done | Chart 2 interactions defined | 27 Sep 2026 (Day 0) | Click-to-filter (with release) defined, drilling the whole page down to a single store (Meeting 2, Interactive Features table).
S2-12 | Write Chart 2 rationale | Ilamperuma | High | Done | Chart 2 design-rationale note | 27 Sep 2026 (Day 0) | Ranked table confirmed: Hell's Kitchen $236,511 → Astoria $232,244 → Lower Manhattan $230,057; spread $6,454; 1.44 units per transaction (Meeting 2, Section 11).
S2-13 | Analyse Chart 3 variables | De Silva | High | Done | Confirmed variable encoding for Chart 3 (Scatter Plot) | 28 Sep 2026 (Day 1) | Variables confirmed per Sprint 1 spec: X-axis = quantity_sold, Y-axis = revenue, colour = store_location. Closed Day 1, per actual Trello checklist count (Burndown, Day 1). | Chart 3 ownership unchanged since Meeting 01 — De Silva.
S2-14 | Create Chart 3 prototype | De Silva | High | Done | Chart 3 prototype built | 29 Sep 2026 (Day 2) | Prototype built plotting daily units sold vs. revenue across the three stores. Closed Day 2, per actual Trello checklist count (Burndown, Day 2).
S2-15 | Decide Chart 3 interactions | De Silva | High | Done | Chart 3 interactions defined | 30 Sep 2026 (Day 3) | Drag-to-zoom defined, letting the user box-select a cluster of points among 56+ store-days plotted (Meeting 2, Interactive Features table). Closed Day 3, per actual Trello checklist count.
S2-16 | Write Chart 3 rationale | De Silva | High | Done | Chart 3 design-rationale note | 30 Sep 2026 (Day 3) | Rationale includes a linear trendline with equation and R² per the Sprint 1 chart spec. Closed Day 3, per actual Trello checklist count.
S2-17 | Review three prototypes together | All | High | Done | Joint review notes and agreed changes | 1 Oct 2026 (Day 4) | Joint review of Chart 1, Chart 2 and Chart 3 prototypes held; cross-chart consistency (shared colour and interaction patterns) agreed at this stage rather than upfront (Retrospective §4). | Delayed to near end of sprint because Chart 3 started later than Chart 1/2.
S2-18 | Confirm common UI design | All | High | Done | Shared colour palette, typography and layout direction for all three charts | 2 Oct 2026 (Day 5) | Common UI design confirmed ahead of Sprint 3 D3.js development (Meeting 2, Section8; Retrospective Section 1).
S2-19 | Prepare progress review | All | High | Done | Short progress summary for Meeting 03 | 3 Oct 2026 (Day 6) | Progress-review update for Meeting 03 prepared on the final sprint day. Closed Day 6, per actual Trello checklist count (Burndown, Day 6). | Pushed to the very last day of the sprint as a result of the Chart 3 delay (Retrospective Section 4).