CIS4014 – Interactive Visualization

Sprint 2 Retrospective

Group: Group 4 | Team of 3 Members

| Field | Details |
| --- | --- |
| Sprint | Sprint 2 – Data Preparation & Visualization Prototyping |
| Duration | 27 September 2026 – 3 October 2026 |
| Sprint Goal | Complete data cleaning and documentation, build and validate a working prototype for each of the three charts, and align the team on a common UI design ahead of Sprint 3. |
| Team Size | 3 members |

# 1. Sprint Goal

The goal of Sprint 2 was to move from project setup into substantive data and visualization work. Building on the Sprint 1 foundation, the team completed detailed cleaning and documentation of the dataset, then designed, built, and validated an initial prototype for each of the three planned charts. The sprint closed with a joint review of the prototypes and agreement on a common UI design, ready to move into refinement and integration in Sprint 3.

# 2. Planned Sprint Work

| Area | Tasks | Planned Work |
| --- | --- | --- |
| Data | S2-01–S2-04 | Complete detailed data cleaning, process the dataset, create a data dictionary, and document the data source. |
| Chart 1 | S2-05–S2-08 | Analyze the variables, build a prototype, define interactions, and write the design rationale for Chart 1. |
| Chart 2 | S2-09–S2-12 | Analyze the variables, build a prototype, define interactions, and write the design rationale for Chart 2. |
| Chart 3 | S2-13–S2-16 | Analyze the variables, build a prototype, define interactions, and write the design rationale for Chart 3. |
| Team / Review | S2-17–S2-19 | Jointly review the three prototypes, confirm a common UI design, and prepare for the Sprint 3 progress review. |

# 3. What Went Well

- The full dataset (~149,000 rows) was cleaned and processed ahead of expectations, with the data dictionary and data-source documentation completed alongside it.

- Chart 1 and Chart 2 prototypes were both completed with validated variable encodings, defined interactions, and a written design rationale, giving the team two working references early in the sprint.

- Early completion of the data-cleaning stream freed up time for prototyping, and the burndown tracked consistently ahead of the planned pace for most of the sprint.

- The team held a structured kickoff (Meeting 02) that reviewed Sprint 1 outcomes and clearly re-scoped the remaining Sprint 2 work, which kept the rest of the sprint focused.

- Trello and GitHub continued to be used consistently for task tracking and version control, carrying forward the good habits established in Sprint 1.

# 4. What Did Not Go Well

- Chart 3 lagged behind Chart 1 and Chart 2: it was still in progress at the Sprint 2 kickoff and needed the bulk of the remaining sprint time to reach prototype and rationale stage.

- Because Chart 3 started later, the joint review of all three prototypes and the common UI design sign-off could not happen until near the end of the sprint, leaving less buffer than planned.

- Progress-review preparation for Meeting 03 was pushed to the very last day of the sprint as a result.

- As in Sprint 1, coordinating three concurrent chart workstreams with a small team required careful scheduling, and some cross-chart consistency decisions (e.g. shared colour and interaction patterns) were left until the review stage rather than agreed upfront.

# 5. Lessons Learned

- Starting all three chart workstreams in parallel from day one, rather than letting one begin only once others are well underway, would reduce the risk of one chart becoming the critical path.

- Agreeing shared design conventions (color palette, interaction style, UI layout) before individual prototyping begins would avoid deferring those decisions to a late joint review.

- Finishing data cleaning and documentation early is valuable and should be preserved as a Sprint 3 habit — it directly enabled faster progress on the two charts that started first.

- Scheduling the joint prototype review and progress-review preparation as a mid-sprint checkpoint, not just an end-of-sprint activity, would reduce last-day pressure.

# 6. Actions for Sprint 3

| ID | Action | Owner |
| --- | --- | --- |
| A1 | Refine all three chart prototypes based on the joint review feedback and agreed common UI design. | Team |
| A2 | Integrate the three charts into a single, consistently styled dashboard view. | Team |
| A3 | Re-validate variable encodings and interactions once the charts are combined. | Samarakoon and De Silva |
| A4 | Plan and begin usability/feedback testing of the combined visualization. | Team |
| A5 | Keep Trello statuses and Scrum evidence up to date throughout Sprint 3. | Team Lead – Ilamperuma |
| A6 | Commit project work to GitHub regularly with clear messages. | Team |

# 7. Retrospective Conclusion

Sprint 2 delivered a cleaned, documented dataset and three chart prototypes, meeting the sprint goal despite Chart 3 taking longer than the other two. The joint review and common UI agreement give the team a consistent basis to build on. Sprint 3 will focus on refining and integrating the three charts into a single dashboard, re-validating the combined design, and beginning usability testing, while keeping Trello, GitHub, and Scrum evidence up to date.

# 8. Team Confirmation

| Member | Name | Student Number | Confirmation |
| --- | --- | --- | --- |
| Member 1 | Imasha Chathurangi Ilamperuma | Team Leader | 4 October 2026 |
| Member 2 | Singappuli Arachchige Isuru Dayanga Samarakoon | Team Member | 4 October 2026 |
| Member 3 | Wijaya Hewage Matheesha Priyan Harshana De Silva | Team Member | 4 October 2026 |