## Sprint 4 Burndown
Day | Date | Planned Remaining | Actual Remaining | Completed Today | Notes
Day 0 | 2026-10-11 | 20 | 20 | 0 | Sprint 4 starts (Meeting 04, 11 Oct 2026); 20 backlog items planned (S4-01 to S4-20). All items Not Started at kickoff, per Meeting 4 action items; no work closed on Day 0.
Day 1 | 2026-10-12 | 17 | 19 | 1 | Common dashboard layout (S4-04) closed: KPI band, shared filter bar and chart panels placed on one page using the common CSS; due Day 1 per Meeting 4 sprint plan.
Day 2 | 2026-10-13 | 13 | 16 | 3 | Chart 1 (S4-01), Chart 2 (S4-02) and Chart 3 (S4-03) integrated full width into the shared layout on the common dataset; all three due Day 2 per Meeting 4 sprint plan.
Day 3 | 2026-10-14 | 10 | 14 | 2 | Common Store / Category / Month filters (S4-05) and Reset button (S4-06) closed; due Day 3 per Meeting 4 sprint plan, alongside the mid-sprint integration checkpoint.
Day 4 | 2026-10-15 | 7 | 11 | 3 | Charts connected (S4-07) and interactions synchronised (S4-08) closed; due Day 4 per Meeting 4 sprint plan. Functional testing (S4-09) closed, start of the Day 4-5 testing window.
Day 5 | 2026-10-16 | 3 | 5 | 6 | Data validation (S4-10), tooltip (S4-11), filter (S4-12) and cross-chart testing (S4-13) closed; due Day 5. Browser testing (S4-14) and bug recording (S4-17) closed within the Day 5-6 and Day 4-6 windows.
Day 6 | 2026-10-17 | 0 | 0 | 5 | Sprint end. Responsive (S4-15) and usability testing (S4-16), high-priority bug fixes (S4-18), retests (S4-19) and testing documentation (S4-20) closed; due Day 6 / end of Week 04. Sprint 4 Backlog fully Done (Product Backlog Sprint Task Log).

## Task Register
ID | Category | Task | Priority | Initial Status | Completed? | Allocated | Day Number
S4-01 | Integration | Integrate Chart 1 | High | To Do | Yes | All | 2
S4-02 | Integration | Integrate Chart 2 | High | To Do | Yes | All | 2
S4-03 | Integration | Integrate Chart 3 | High | To Do | Yes | All | 2
S4-04 | Integration | Create common dashboard layout | High | To Do | Yes | All | 1
S4-05 | Integration | Add common filters | High | To Do | Yes | All | 3
S4-06 | Integration | Add Reset button | High | To Do | Yes | All | 3
S4-07 | Integration | Connect charts | High | To Do | Yes | All | 4
S4-08 | Integration | Synchronise interactions | High | To Do | Yes | All | 4
S4-09 | Testing | Functional testing | High | To Do | Yes | All | 4
S4-10 | Testing | Data validation | High | To Do | Yes | All | 5
S4-11 | Testing | Tooltip testing | High | To Do | Yes | All | 5
S4-12 | Testing | Filter testing | High | To Do | Yes | All | 5
S4-13 | Testing | Cross-chart testing | High | To Do | Yes | All | 5
S4-14 | Testing | Browser testing | High | To Do | Yes | All | 5
S4-15 | Testing | Responsive testing | High | To Do | Yes | All | 6
S4-16 | Testing | Usability testing | High | To Do | Yes | All | 6
S4-17 | Bug Fixing | Record bugs | High | To Do | Yes | All | 5
S4-18 | Bug Fixing | Fix high-priority bugs | High | To Do | Yes | All | 6
S4-19 | Bug Fixing | Retest fixes | High | To Do | Yes | All | 6
S4-20 | Bug Fixing | Update testing documentation | High | To Do | Yes | All | 6

## Instructions
Item | Instruction
Purpose | Use this workbook as Sprint 4 burndown evidence.
Initial workload | Sprint 4 contains 20 backlog items (S4-01 to S4-20), per the Product Backlog / Sprint Task Log.
Day 0 starting point | Day 0 (11 Oct 2026) reflects Meeting 04 (Sprint 4 kickoff): every Sprint 4 action item was recorded as Not Started, so all 20 items are open on Day 0 and none is closed at kickoff.
Daily update | At the end of each working day, count unchecked Sprint 3 checklist items in Trello and enter that number in Actual Remaining.
Completed Today | This column calculates daily completion from the Actual Remaining values.
Important | Do not invent actual progress. Use the real Trello checklist count.
Chart | The planned and actual lines both update automatically from the table.
Evidence | Keep dated Trello screenshots or board history if your lecturer requires progress evidence.