## Sprint 1 Burndown
Day | Date | Planned Remaining | Actual Remaining | Completed Today | Notes
Day 0 | 2026-09-20 | 20 | 15 | 5 | Sprint starts; 20 checklist items planned.
Day 1 | 2026-09-21 | 17 | 12 | 3 | Enter actual remaining items from Trello.
Day 2 | 2026-09-22 | 13 | 9 | 3 | Enter actual remaining items from Trello.
Day 3 | 2026-09-23 | 10 | 7 | 2 | Enter actual remaining items from Trello.
Day 4 | 2026-09-24 | 7 | 4 | 3 | Enter actual remaining items from Trello.
Day 5 | 2026-09-25 | 4 | 2 | 2 | Enter actual remaining items from Trello.
Day 6 | 2026-09-26 | 0 | 2 | 0 | Sprint end; enter actual remaining items from Trello.

## Task Register
ID | Category | Task | Priority | Initial Status | Completed? | Allocated | Day Number
S1-01 | Planning | Review assessment requirements | High | To Do | No | All | 0
S1-02 | Planning | Select project topic | High | To Do | No | All | 0
S1-03 | Planning | Select dataset | High | To Do | No | All | 0
S1-04 | Planning | Identify target audience | Medium | To Do | No | All | 0
S1-05 | Planning | Define overarching research question | High | To Do | No | All | 0
S1-06 | Planning | Define Chart 1 research question | High | To Do | No | Samarakoon | 1
S1-07 | Planning | Define Chart 2 research question | High | To Do | No | Ilamperuma | 1
S1-08 | Planning | Define Chart 3 research question | High | To Do | No | De Silva | 1
S1-09 | Visualisation Planning | Select Chart 1 type | High | To Do | No | Samarakoon | 2
S1-10 | Visualisation Planning | Select Chart 2 type | High | To Do | No | Ilamperuma | 2
S1-11 | Visualisation Planning | Select Chart 3 type | High | To Do | No | De Silva | 2
S1-12 | Project Management | Create Trello board | High | To Do | No | Ilamperuma | 3
S1-13 | Project Management | Add team members | Medium | To Do | No | Ilamperuma | 3
S1-14 | Project Management | Create GitHub repository | High | To Do | No | Ilamperuma | 4
S1-15 | Project Management | Add team members to GitHub | Medium | To Do | No | Ilamperuma | 4
S1-16 | Project Management | Create GitHub folder structure | Medium | To Do | No | Ilamperuma | 4
S1-17 | Data | Initial dataset analysis | High | To Do | No | All | 5
S1-18 | Data | Identify missing/duplicate data | High | To Do | No | All | 5
S1-19 | Documentation | Prepare Meeting 01 minutes | Medium | To Do | No | Ilamperuma | 6
S1-20 | Documentation | Prepare Sprint 1 documentation | Medium | To Do | No | Ilamperuma | 6

## Instructions
Item | Instruction
Purpose | Use this workbook as Sprint 1 burndown evidence.
Initial workload | Sprint 1 contains 20 checklist items (S1-01 to S1-20).
Daily update | At the end of each working day, count unchecked Sprint 1 checklist items in Trello and enter that number in Actual Remaining.
Completed Today | This column calculates daily completion from the Actual Remaining values.
Important | Do not invent actual progress. Use the real Trello checklist count.
Chart | The planned line is already included; the actual line appears as values are entered.
Evidence | Keep dated Trello screenshots or board history if your lecturer requires progress evidence.