## Sprint 1 Burndown
Day | Date | Planned Remaining | Actual Remaining | Completed Today | Notes
Day 0 | 2026-09-20 | 20 | 15 | 5 | Sprint 1 starts; 20 checklist items planned. Review assessment requirements, Select project topic, Select dataset, Identify target audience, and Define overarching research question (S1-01 to S1-05) closed today, per actual Trello count.
Day 1 | 2026-09-21 | 17 | 12 | 3 | Define Chart 1, Chart 2, and Chart 3 research questions (S1-06 to S1-08) closed today, per actual Trello count.
Day 2 | 2026-09-22 | 13 | 9 | 3 | Select Chart 1, Chart 2, and Chart 3 types (S1-09 to S1-11) closed today, per actual Trello count.
Day 3 | 2026-09-23 | 10 | 7 | 2 | Create Trello board and add team members (S1-12, S1-13) closed today, per actual Trello count.
Day 4 | 2026-09-24 | 7 | 4 | 3 | Create GitHub repository, add team members to GitHub, and create GitHub folder structure (S1-14 to S1-16) closed today, per actual Trello count.
Day 5 | 2026-09-25 | 4 | 2 | 2 | Initial dataset analysis and identify missing/duplicate data (S1-17, S1-18) closed today, per actual Trello count.
Day 6 | 2026-09-26 | 0 | 2 | 0 | Sprint end. Prepare Meeting 01 minutes and Prepare Sprint 1 documentation (S1-19, S1-20) .

## Task Register
ID | Category | Task | Priority | Initial Status | Completed? | Allocated | Day Number
S1-01 | Planning | Review assessment requirements | High | To Do | Yes | All | 0
S1-02 | Planning | Select project topic | High | To Do | Yes | All | 0
S1-03 | Planning | Select dataset | High | To Do | Yes | All | 0
S1-04 | Planning | Identify target audience | Medium | To Do | Yes | All | 0
S1-05 | Planning | Define overarching research question | High | To Do | Yes | All | 0
S1-06 | Planning | Define Chart 1 research question | High | To Do | Yes | Samarakoon | 1
S1-07 | Planning | Define Chart 2 research question | High | To Do | Yes | Ilamperuma | 1
S1-08 | Planning | Define Chart 3 research question | High | To Do | Yes | De Silva | 1
S1-09 | Visualisation Planning | Select Chart 1 type | High | To Do | Yes | Samarakoon | 2
S1-10 | Visualisation Planning | Select Chart 2 type | High | To Do | Yes | Ilamperuma | 2
S1-11 | Visualisation Planning | Select Chart 3 type | High | To Do | Yes | De Silva | 2
S1-12 | Project Management | Create Trello board | High | To Do | Yes | Ilamperuma | 3
S1-13 | Project Management | Add team members | Medium | To Do | Yes | Ilamperuma | 3
S1-14 | Project Management | Create GitHub repository | High | To Do | Yes | Ilamperuma | 4
S1-15 | Project Management | Add team members to GitHub | Medium | To Do | Yes | Ilamperuma | 4
S1-16 | Project Management | Create GitHub folder structure | Medium | To Do | Yes | Ilamperuma | 4
S1-17 | Data | Initial dataset analysis | High | To Do | Yes | All | 5
S1-18 | Data | Identify missing/duplicate data | High | To Do | Yes | All | 5
S1-19 | Documentation | Prepare Meeting 01 minutes | Medium | To Do | Yes | Ilamperuma | 6
S1-20 | Documentation | Prepare Sprint 1 documentation | Medium | To Do | Yes | Ilamperuma | 6

## Instructions
Item | Instruction
Purpose | Use this workbook as Sprint 1 burndown evidence.
Initial workload | Sprint 1 contains 20 checklist items (S1-01 to S1-20).
Day 0 starting point | Day 0 (20 Sep 2026) is the Sprint 1 kickoff, when all 20 checklist items (S1-01 to S1-20) were open. Five planning items were closed on Day 0 per the actual Trello count (S1-01 to S1-05: review assessment requirements, select project topic, select dataset, identify target audience, define overarching research question), leaving 15 items open at the end of Day 0.
Daily update | At the end of each working day, count unchecked Sprint 1 checklist items in Trello and enter that number in Actual Remaining.
Completed Today | This column calculates daily completion from the Actual Remaining values.
Important | Do not invent actual progress. Use the real Trello checklist count.
Chart | The planned line is already included; the actual line appears as values are entered.
Evidence | Keep dated Trello screenshots or board history if your lecturer requires progress evidence.