## Sprint 5 Burndown
Day | Date | Planned Remaining | Actual Remaining | Completed Today | Notes
Day 0 | 2026-10-18 | 20 | 20 | 0 | Sprint 5 starts (Meeting 05, 18 Oct 2026); 20 backlog items planned (S5-01 to S5-20). All items Not Started at kickoff, per Meeting 5 action items; no work closed on Day 0.
Day 1 | 2026-10-19 | 17 | 17 | 3 | Final UI review, chart-label and tooltip checks (S5-01, S5-02, S5-03) closed; due Day 1 per Meeting 5 sprint plan.
Day 2 | 2026-10-20 | 13 | 14 | 3 | Filter, Reset button and cross-chart interaction checks (S5-04, S5-05, S5-06) closed; due Day 2 per Meeting 5 sprint plan.
Day 3 | 2026-10-21 | 10 | 13 | 1 | Responsive layout check (S5-07) closed, completing the final website checks; due Day 3, alongside the mid-sprint checkpoint reviewing all website checks together.
Day 4 | 2026-10-22 | 7 | 9 | 4 | Ethical review closed: misleading-axes and calculation checks (S5-08, S5-09) and data-source attribution and limitations checks (S5-10, S5-11); due Day 4 per Meeting 5 sprint plan.
Day 5 | 2026-10-23 | 3 | 3 | 6 | Remaining documentation closed: Scrum, meeting minutes, testing, design rationale and design requirements documentation, and the README update (S5-12 to S5-17); due Day 5.
Day 6 | 2026-10-24 | 0 | 0 | 3 | Sprint end. GitHub repository check (S5-18) and final team review (S5-19) closed; due Day 6. Submission (S5-20) prepared immediately after. Sprint 5 Backlog fully Done (Product Backlog Sprint Task Log).

## Task Register
ID | Category | Task | Priority | Initial Status | Completed? | Allocated | Day Number
S5-01 | Final Website | Final UI review | High | To Do | Yes | Samarakoon | 1
S5-02 | Final Website | Check chart labels | High | To Do | Yes | Samarakoon | 1
S5-03 | Final Website | Check tooltips | High | To Do | Yes | Samarakoon | 1
S5-04 | Final Website | Check filters | High | To Do | Yes | Ilamperuma | 2
S5-05 | Final Website | Check Reset button | High | To Do | Yes | Ilamperuma | 2
S5-06 | Final Website | Check cross-chart interaction | High | To Do | Yes | Ilamperuma | 2
S5-07 | Final Website | Check responsive layout | High | To Do | Yes | De Silva | 3
S5-08 | Ethical Review | Check for misleading axes | High | To Do | Yes | Samarakoon | 4
S5-09 | Ethical Review | Verify calculations | High | To Do | Yes | Samarakoon | 4
S5-10 | Ethical Review | Check data-source attribution | High | To Do | Yes | De Silva | 4
S5-11 | Ethical Review | Document limitations | High | To Do | Yes | De Silva | 4
S5-12 | Documentation | Complete Scrum documentation | High | To Do | Yes | Ilamperuma | 5
S5-13 | Documentation | Complete meeting minutes | High | To Do | Yes | Ilamperuma | 5
S5-14 | Documentation | Complete testing documentation | High | To Do | Yes | Ilamperuma | 5
S5-15 | Documentation | Complete design rationale documentation | High | To Do | Yes | Ilamperuma | 5
S5-16 | Documentation | Complete design requirements documentation | High | To Do | Yes | Ilamperuma | 5
S5-17 | Documentation | Update README | High | To Do | Yes | Ilamperuma | 5
S5-18 | Final Review & Submission | Check GitHub repository | High | To Do | Yes | Ilamperuma | 6
S5-19 | Final Review & Submission | Final team review | High | To Do | Yes | All | 6
S5-20 | Final Review & Submission | Prepare submission | High | To Do | Yes | All | 6

## Instructions
Item | Instruction
Purpose | Use this workbook as Sprint 5 burndown evidence.
Initial workload | Sprint 5 contains 20 backlog items (S5-01 to S5-20), per the Product Backlog / Sprint Task Log.
Day 0 starting point | Day 0 (18 Oct 2026) reflects Meeting 05 (Sprint 5 kickoff): every Sprint 5 action item was recorded as Not Started, so all 20 items are open on Day 0 and none is closed at kickoff.
Daily update | At the end of each working day, count unchecked Sprint 5 checklist items in Trello and enter that number in Actual Remaining.
Completed Today | This column calculates daily completion from the Actual Remaining values.
Important | Do not invent actual progress. Use the real Trello checklist count.
Chart | The planned and actual lines both update automatically from the table.
Evidence | Keep dated Trello screenshots or board history if your lecturer requires progress evidence.