## Sprint 4
CIS4014-N Interactive Visualisation – Group 4 ¦ Sprint 4 – Week 04
Sprint | Sprint 4
Duration | Week 04 (11 October 2026 – 17 October 2026)
Sprint Goal | Integrate the three D3.js charts into a single dashboard on the confirmed common layout, add the shared Store / Category / Month filters and Reset button, connect the charts and synchronise their interactions, and complete functional, data validation, tooltip, filter, cross-chart, browser, responsive and usability testing with bug fixing, ahead of the final website checks and submission in Sprint 5.
Team Leader | Imasha Chathurangi Ilamperuma (F5692459)
Other Team Members | Singappuli Arachchige Isuru Dayanga Samarakoon - F5692600 , Wijaya Hewage Matheesha Priyan Harshana De Silva - F5692734
Project Management Tool | Trello
Version Control | GitHub
Task ID | Sprint Task | Assigned To | Priority | Status | Expected Output | Due | Notes / Evidence | Additional Comments
S4-01 | Integrate Chart 1 into the dashboard | All (lead: Samarakoon) | High | Done | D3.js Temporal Heat Map running full width inside the shared layout on the common dataset | 13 Oct 2026 (Day 2) | Chart 1 (7 days × 15 hourly columns) placed full width in the shared layout on the cleaned dataset (149,116 rows × 23 columns), keeping the encoding validated in its Excel prototype, with its tooltip and hover-to-isolate / click-to-hold interaction.
S4-02 | Integrate Chart 2 into the dashboard | All (lead: Ilamperuma) | High | Done | D3.js Store Location Map running full width inside the shared layout on the common dataset | 13 Oct 2026 (Day 2) | Chart 2 (bubble map: position = geography, bubble size = revenue) placed full width in the shared layout on the common dataset, keeping its tooltip and click-to-filter (with release) interaction.
S4-03 | Integrate Chart 3 into the dashboard | All (lead: De Silva) | High | Done | D3.js Scatter Plot running full width inside the shared layout on the common dataset | 13 Oct 2026 (Day 2) | Chart 3 (X = quantity sold, Y = revenue, colour = store location) placed full width in the shared layout on the common dataset, keeping its tooltip and drag-to-zoom box-select interaction.
S4-04 | Create common dashboard layout | All (lead: Ilamperuma) | High | Done | Single page with KPI band, shared filter bar and chart panels placed as confirmed in Meeting 04, using the common CSS | 12 Oct 2026 (Day 1) | KPI band (revenue, transactions, units sold, per-transaction value, busiest hour), shared filter bar and chart panels placed on one page using the common CSS, following the dashboard integration design confirmed at Meeting 04 (Section 6). | https://github.com/inkymello/group4-interactive-visualisation/tree/main/web
S4-05 | Add common filters | All (lead: Ilamperuma) | High | Done | Store / Category / Month filter bar driving all three charts and the KPI band | 14 Oct 2026 (Day 3) | Shared Store / Category / Month filters apply to all three charts and the KPI band together, rather than to each chart separately (Meeting 04, Section 6). Closed on the day of the mid-sprint integration checkpoint. | https://github.com/inkymello/group4-interactive-visualisation/tree/main/web
S4-06 | Add Reset button | All (lead: Ilamperuma) | High | Done | Reset button returning all filters and chart selections to the default view | 14 Oct 2026 (Day 3) | One click clears every active filter and any held or selected chart state (held hour, selected store, zoom) and returns the dashboard to its default view. | https://github.com/inkymello/group4-interactive-visualisation/tree/main/web
S4-07 | Connect charts | All (lead: Ilamperuma) | High | Done | A selection in one chart updates the other charts and the KPI band | 15 Oct 2026 (Day 4) | Selecting a store on the map (click-to-filter) updates the KPI band, heat map and scatter plot; releasing the selection returns all charts to the current filter state (Meeting 04, Section 6). | https://github.com/inkymello/group4-interactive-visualisation/tree/main/web
S4-08 | Synchronise interactions | All (lead: Ilamperuma) | High | Done | Identical hover, highlight and transition behaviour, linked across all three charts | 15 Oct 2026 (Day 4) | Hover/tooltip style, transition timing and highlight colour made identical across the connected charts, with store accents following the finalised palette: Hell's Kitchen #E0705F, Astoria #E4A94D, Lower Manhattan #58B09C. | https://github.com/inkymello/group4-interactive-visualisation/tree/main/web
S4-09 | Functional testing | All | High | Done | Dashboard behaviour checked across the integrated charts, filters and Reset button | 15 Oct 2026 (Day 4) | Closed on Day 4, at the start of the Day 4–5 testing window, once the charts were connected and their interactions synchronised (S4-07, S4-08). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-10 | Data validation | All | High | Done | Displayed figures checked against the cleaned dataset and Excel prototype values | 16 Oct 2026 (Day 5) | Dashboard figures checked against the cleaned dataset and the values validated in the Excel prototypes (e.g. KPI band: $698,812 revenue, 149,116 transactions, 214,470 units). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-11 | Tooltip testing | All | High | Done | Tooltips tested across all three charts | 16 Oct 2026 (Day 5) | Tooltips for the heat map (exact day/hour counts), store map (store revenue/transaction detail) and scatter plot (daily units/revenue detail) tested in the integrated dashboard. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-12 | Filter testing | All | High | Done | Shared Store / Category / Month filters tested across all three charts and the KPI band | 16 Oct 2026 (Day 5) | Shared filters and Reset button tested to confirm they drive all three charts and the KPI band together. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-13 | Cross-chart testing | All | High | Done | Linked selections tested across all three charts | 16 Oct 2026 (Day 5) | Store selection on the map and its release tested for their effect on the KPI band, heat map and scatter plot. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-14 | Browser testing | All | High | Done | Dashboard tested across browsers | 16 Oct 2026 (Day 5) | Closed on Day 5, within the Day 5–6 window in the Meeting 04 sprint plan. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-15 | Responsive testing | All | High | Done | Dashboard tested across screen sizes | 17 Oct 2026 (Day 6) | Closed on Day 6, within the Day 5–6 window in the Meeting 04 sprint plan. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-16 | Usability testing | All | High | Done | Usability feedback on the combined dashboard recorded | 17 Oct 2026 (Day 6) | Closed on Day 6, within the Day 5–6 window in the Meeting 04 sprint plan. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-17 | Record bugs | All | High | Done | Bug log kept as testing proceeds | 16 Oct 2026 (Day 5) | Bug log opened as testing proceeded (plan window Day 4–6) and closed on Day 5, so that fixes could start before the end of the sprint. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-18 | Fix high-priority bugs | All | High | Done | High-priority bugs from the bug log fixed | 17 Oct 2026 (Day 6) | High-priority bugs from the bug log fixed on Day 6 (plan window Day 4–6). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-19 | Retest fixes | All | High | Done | Fixed bugs retested | 17 Oct 2026 (Day 6) | Fixes retested on Day 6 (plan window Day 4–6). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S4-20 | Update testing documentation | All | High | Done | Testing results, bug log and retest outcomes documented | 17 Oct 2026 (Day 6) | Testing results, bug log and retest outcomes written into the testing documentation by the end of Week 04. Sprint 4 Backlog fully Done; burndown finished at 0 of 20 items remaining. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx