## Sprint 1
CIS4014-N Interactive Visualisation – Group 4 ¦ Sprint 1 – Week 01
Sprint | Sprint 1
Duration | Week 01
Sprint Goal | Establish the project foundation: select the topic and dataset, define research questions, agree chart types, and set up Trello and GitHub.
Team Leader | Imasha Chathurangi Ilamperuma (F5692459)
Other Team Members | Singappuli Arachchige Isuru Dayanga Samarakoon - F5692600 , Wijaya Hewage Matheesha Priyan Harshana De Silva - F5692734
Project Management Tool | Trello
Version Control | GitHub
Task ID | Sprint Task | Assigned To | Priority | Status | Expected Output | Due | Notes / Evidence | Additional Comments
S1-01 | Review assessment requirements | All | High | Done | Shared understanding of requirements | Week 01 | Recorded key requirements in meeting minutes
S1-02 | Discuss and select project topic | All | High | Done | Agreed project topic | Week 01 | Documened final decision | The morning rush pays for the day
S1-03 | Select suitable dataset | All | High | Done | Selected dataset and source | Week 01 | Coffe Shop Sales Dataset | https://github.com/inkymello/group4-interactive-visualisation/blob/main/data/Coffee%20Shop%20Sales-Raw%20Data.xlsx
S1-04 | Identify target audience | All | Medium | Done | Defined target audience | Week 01 | Coffee shop owners, managers, and business decision-makers who want to understand sales patterns and use transaction data to support business decisions.
S1-05 | Define overarching research question | All | High | Done | One team-level research question | Week 01 | Connected all three charts | How do coffee shop sales vary in terms of when customers buy, where revenue is generated, and the relationship between units sold and daily revenue during the morning rush?
S1-06 | Define individual research question – Chart 1 | Samarakoon | High | Done | Chart 1 research question | Week 01 | Confirmed suitable variables | Rows: day_of_week (Monday–Sunday) ,Columns: hour, Cell value / color: transaction count for that day-hour combination
S1-07 | Define individual research question – Chart 2 | Ilamperuma | High | Done | Chart 2 research question | Week 01 | Confirmed suitable variables | X-axis: longitude,Y-axis: latitude,Bubble size: revenue,Series/legend: store_location,(Ranking table alongside also shows revenue and transactions per store)
S1-08 | Define individual research question – Chart 3 | De Silva | High | Done | Chart 3 research question | Week 01 | Confirmed suitable variables | X-axis: quantity_sold (units sold per day),Y-axis: revenue (revenue per day),Series/color: store_location,Trendline: linear fit on the data, with equation and R² displayed
S1-09 | Select chart type – Chart 1 | Samarakoon | High | Done | Chart 1 type and rationale | Week 01 | Temporal Heat Map
S1-10 | Select chart type – Chart 2 | Ilamperuma | High | Done | Chart 2 type and rationale | Week 01 | Store Location Map
S1-11 | Select chart type – Chart 3 | De Silva | High | Done | Chart 3 type and rationale | Week 01 | Scatter Plot
S1-12/S1-13 | Create Trello board and invite team | Ilamperuma | High | Done | Shared Trello board | Day 1–2 | https://trello.com/b/k5MT44Ww/group-4-cis4014-n-interactive-visualisation
S1-14/S1-15 | Create GitHub repository and invite team | Ilamperuma | High | Done | Shared GitHub repository | Day 1–2 | https://github.com/inkymello/group4-interactive-visualisation
S1-16 | Create initial GitHub folder structure | Ilamperuma | Medium | Done | Project folders created | Week 01 | https://github.com/inkymello/group4-interactive-visualisation/blob/main/README_STRUCTURE.md
S1-17 | Initial dataset analysis | All | High | Done | Variable and data-quality notes | Week 01 | https://github.com/inkymello/group4-interactive-visualisation/blob/main/data/Coffee_Shop%20Sales%20-Cleaned%20and%20Processed%20Data.xlsx | Refer to the data Cleaning Log Sheet
S1-18 | Create initial Product Backlog | Ilamperuma | High | Done | Master task list | Week 01 | Maintained in Trello | https://trello.com/b/k5MT44Ww/group-4-cis4014-n-interactive-visualisation
S1-19 | Prepare Meeting 01 minutes | Ilamperuma | Medium | Done | Meeting_01.docx | Week 01 | Uploaded to documentation/meetings to github | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/meetings/Meeting_01.docx
S1-20 | Agree Week 02 priorities | Ilamperuma | Medium | Done | Next sprint priorities | End of Week 01 | Discussed at sprint review