## Sprint 2 Burndown
Day | Date | Planned Remaining | Actual Remaining | Completed Today | Notes
Day 0 | 2026-09-27 | 19 | 7 | 12 | Sprint 2 starts (Meeting 02, 27 Sep 2026); 19 backlog items planned. Data cleaning (S2-01 to S2-04), Chart 1 prototype/rationale (S2-05 to S2-08), and Chart 2 prototype/rationale (S2-09 to S2-12) closed at kickoff, per Meeting 2 minutes.
Day 1 | 2026-09-28 | 16 | 6 | 1 | Chart 3 variable analysis (S2-13) closed today, per actual Trello count.
Day 2 | 2026-09-29 | 13 | 5 | 1 | Chart 3 prototype (S2-14) closed today, per actual Trello count.
Day 3 | 2026-09-30 | 10 | 3 | 2 | Chart 3 interactions and rationale (S2-15, S2-16) closed today, per actual Trello count.
Day 4 | 2026-10-01 | 6 | 2 | 1 | Joint review of the three prototypes (S2-17) closed today, per actual Trello count.
Day 5 | 2026-10-02 | 3 | 1 | 1 | Common UI design sign-off (S2-18) closed today, per actual Trello count.
Day 6 | 2026-10-03 | 0 | 0 | 1 | Sprint end. Progress-review prep for Meeting 03 (S2-19) closed today, per actual Trello count.

## Task Register
ID | Category | Task | Priority | Initial Status | Completed? | Allocated | Day Number
S2-01 | Data | Complete data cleaning | High | To Do | Yes | All | 0
S2-02 | Data | Process dataset | High | To Do | Yes | All | 0
S2-03 | Data | Create data dictionary | High | To Do | Yes | All | 0
S2-04 | Data | Document data source | High | To Do | Yes | All | 0
S2-05 | Chart 1 | Analyse Chart 1 variables | High | To Do | Yes | Samarakoon | 0
S2-06 | Chart 1 | Create Chart 1 prototype | High | To Do | Yes | Samarakoon | 0
S2-07 | Chart 1 | Decide Chart 1 interactions | High | To Do | Yes | Samarakoon | 0
S2-08 | Chart 1 | Write Chart 1 rationale | High | To Do | Yes | Samarakoon | 0
S2-09 | Chart 2 | Analyse Chart 2 variables | High | To Do | Yes | Ilamperuma | 0
S2-10 | Chart 2 | Create Chart 2 prototype | High | To Do | Yes | Ilamperuma | 0
S2-11 | Chart 2 | Decide Chart 2 interactions | High | To Do | Yes | Ilamperuma | 0
S2-12 | Chart 2 | Write Chart 2 rationale | High | To Do | Yes | Ilamperuma | 0
S2-13 | Chart 3 | Analyse Chart 3 variables | High | To Do | Yes | De Silva | 1
S2-14 | Chart 3 | Create Chart 3 prototype | High | To Do | Yes | De Silva | 2
S2-15 | Chart 3 | Decide Chart 3 interactions | High | To Do | Yes | De Silva | 3
S2-16 | Chart 3 | Write Chart 3 rationale | High | To Do | Yes | De Silva | 3
S2-17 | Team | Review three prototypes together | High | To Do | Yes | All | 4
S2-18 | Team | Confirm common UI design | High | To Do | Yes | All | 5
S2-19 | Team | Prepare progress review | High | To Do | Yes | All | 6

## Instructions
Item | Instruction
Purpose | Use this workbook as Sprint 2 burndown evidence.
Initial workload | Sprint 2 contains 19 backlog items (S2-01 to S2-19), per the Product Backlog / Sprint Task Log.
Day 0 starting point | Day 0 (27 Sep 2026) reflects the status recorded in Meeting 2 minutes at Sprint 2 kickoff: data cleaning, Chart 1, and Chart 2 (prototype + rationale) already complete (12 of 19 items), leaving 7 items open — Chart 3 prototyping/rationale plus the team's joint prototype review, common UI confirmation, and progress-review prep.
Daily update | At the end of each working day, count unchecked Sprint 2 checklist items in Trello and enter that number in Actual Remaining.
Completed Today | This column calculates daily completion from the Actual Remaining values.
Important | Do not invent actual progress. Use the real Trello checklist count.
Chart | The planned line is already included; the actual line appears as values are entered.
Evidence | Keep dated Trello screenshots or board history if your lecturer requires progress evidence.