## Sprint 5
CIS4014-N Interactive Visualisation – Group 4 ¦ Sprint 5 – Week 05
Sprint | Sprint 5
Duration | Week 05 (18 October 2026 – 24 October 2026)
Sprint Goal | Complete the final website checks (UI review, chart labels, tooltips, shared filters, Reset button, cross-chart interaction and responsive layout) and the ethical review (misleading axes, calculations, data-source attribution and limitations) on the integrated dashboard, complete the remaining Scrum, meeting minutes, testing, design rationale and design requirements documentation and the README, then check the GitHub repository, hold the final team review and prepare the submission, closing the project. No new development in this sprint (Meeting 05, Section 8).
Team Leader | Imasha Chathurangi Ilamperuma (F5692459)
Other Team Members | Singappuli Arachchige Isuru Dayanga Samarakoon - F5692600 , Wijaya Hewage Matheesha Priyan Harshana De Silva - F5692734
Project Management Tool | Trello
Version Control | GitHub
Task ID | Sprint Task | Assigned To | Priority | Status | Expected Output | Due | Notes / Evidence | Additional Comments
S5-01 | Final UI review | All (lead: Ilamperuma) | High | Done | Dashboard visuals confirmed consistent with the common UI design and finalised palette | 19 Oct 2026 (Day 1) | Overall look and consistency of the published dashboard checked against the common UI design and the finalised palette (Meeting 05, Section 6). Closed on Day 1 with S5-02 and S5-03.
S5-02 | Check chart labels | All (lead: Ilamperuma) | High | Done | Titles, axis labels, legend text and units confirmed correct and consistent across all three charts | 19 Oct 2026 (Day 1) | Titles, axis labels, legend text and units checked for correct wording and consistency across the heat map, store map and scatter plot. Closed on Day 1.
S5-03 | Check tooltips | All (lead: Ilamperuma) | High | Done | All three chart tooltips confirmed showing correct figures | 19 Oct 2026 (Day 1) | Heat map (day/hour counts), store map (store revenue/transaction detail) and scatter plot (daily units/revenue detail) tooltips checked for correct figures. Closed on Day 1.
S5-04 | Check filters | All (lead: Ilamperuma) | High | Done | Shared Store / Category / Month filters confirmed narrowing all three charts and the KPI band together | 20 Oct 2026 (Day 2) | Shared Store / Category / Month filters checked to confirm they narrow all three charts and the KPI band together. Closed on Day 2 with S5-05 and S5-06.
S5-05 | Check Reset button | All (lead: Ilamperuma) | High | Done | Reset button confirmed returning all filters and chart selections to the default view | 20 Oct 2026 (Day 2) | One click confirmed to clear every active filter and any held or selected chart state (held hour, selected store, zoom) and return the dashboard to its default view.
S5-06 | Check cross-chart interaction | All (lead: Ilamperuma) | High | Done | Store selection and release confirmed updating all linked views | 20 Oct 2026 (Day 2) | Selecting and releasing a store on the map checked for its effect on the KPI band, heat map and scatter plot.
S5-07 | Check responsive layout | All (lead: Ilamperuma) | High | Done | Dashboard confirmed usable and readable across common screen sizes | 21 Oct 2026 (Day 3) | Closed on Day 3, completing the final website checks (S5-01–S5-07); reviewed together with them at the Day 3 mid-sprint checkpoint before the ethical review began.
S5-08 | Check for misleading axes | All (lead: Ilamperuma) | High | Done | Chart axes confirmed not scaled in a way that exaggerates or understates differences between stores or time periods | 22 Oct 2026 (Day 4) | Chart axes checked to start at zero or otherwise not be scaled misleadingly (Meeting 05, Section 6). Closed on Day 4 with S5-09, S5-10 and S5-11.
S5-09 | Verify calculations | All (lead: Ilamperuma) | High | Done | KPI band, ranking and regression figures confirmed accurate against the cleaned dataset and Excel prototype values | 22 Oct 2026 (Day 4) | Figures re-verified against the cleaned dataset and the Excel-validated values (e.g. KPI band: $698,812 revenue, 149,116 transactions, 214,470 units; scatter trend y = 3.20x + 23.59, R² 0.939).
S5-10 | Check data-source attribution | All (lead: Ilamperuma) | High | Done | Attribution confirmed correct in the dashboard footer and documentation | 22 Oct 2026 (Day 4) | Dashboard footer and documentation checked to credit the cleaned transaction dataset and to state that the basemap is simplified geometry, not a tile service.
S5-11 | Document limitations | All (lead: Ilamperuma) | High | Done | Known limitations recorded in the documentation | 22 Oct 2026 (Day 4) | Known limitations recorded, including the simplified basemap geometry, the six-month data window (January–June 2023) and the single overall (not per-store) scatter trendline.
S5-12 | Complete Scrum documentation | Ilamperuma (reviewed by Samarakoon and De Silva) | High | Done | Scrum records finalised | 23 Oct 2026 (Day 5) | Closed on Day 5 with S5-13 to S5-17, led by Ilamperuma and reviewed by Samarakoon and De Silva before being marked Done (Meeting 05, Section 8). | vvv
S5-13 | Complete meeting minutes | Ilamperuma (reviewed by Samarakoon and De Silva) | High | Done | All meeting minutes finalised | 23 Oct 2026 (Day 5) | Meeting minutes for the project finalised, including Meeting 05 (Sprint 5 kickoff); no Meeting 06 is planned (Meeting 05, Section 10). | https://github.com/inkymello/group4-interactive-visualisation/tree/main/documentation/meetings
S5-14 | Complete testing documentation | Ilamperuma (reviewed by Samarakoon and De Silva) | High | Done | Testing documentation finalised | 23 Oct 2026 (Day 5) | Testing and bug fixing documentation finalised, building on the Sprint 4 testing results, bug log and retest outcomes. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/testing/Testing_Bug_Fixing%20_Documentation.docx
S5-15 | Complete design rationale documentation | Ilamperuma (reviewed by Samarakoon and De Silva) | High | Done | Design rationale documentation finalised | 23 Oct 2026 (Day 5) | Design rationale documentation finalised; chart encodings and common UI design carried over unchanged from Meeting 04. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/design/Design_Rationale.docx
S5-16 | Complete design requirements documentation | Ilamperuma (reviewed by Samarakoon and De Silva) | High | Done | Design requirements documentation finalised | 23 Oct 2026 (Day 5) | Design requirements documentation finalised; the overarching and individual research questions are unchanged from Meeting 04. | https://github.com/inkymello/group4-interactive-visualisation/blob/main/documentation/design/Design_Requirements.docx
S5-17 | Update README | Ilamperuma (reviewed by Samarakoon and De Silva) | High | Done | README reflects the finished dashboard and project structure | 23 Oct 2026 (Day 5) | README updated to reflect the finished dashboard and project structure. Closed on Day 5, the last of the six documentation items (S5-12 to S5-17). | https://github.com/inkymello/group4-interactive-visualisation/blob/main/README.md
S5-18 | Check GitHub repository | All (lead: Ilamperuma) | High | Done | Repository structure, commits and files confirmed complete and organised | 24 Oct 2026 (Day 6) | Repository structure, commits and files checked for completeness and organisation. Closed on Day 6. | https://github.com/inkymello/group4-interactive-visualisation
S5-19 | Final team review | All | High | Done | Whole team signs off the finished dashboard and documentation | 24 Oct 2026 (Day 6) | Closing review of the project held on Day 6 immediately before the submission was prepared (Meeting 05, Section 10). No new checks were started on Day 6. | vvv
S5-20 | Prepare submission | All | High | Done | Submission package assembled and ready to hand in | 24 Oct 2026 (Day 6) | Submission prepared at the end of Day 6. Sprint 5 Backlog fully Done; burndown finished at 0 of 20 items remaining, and the project is complete.